## Check user registration with an
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Check user registration with an existing username | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | User is in the registration page
Dependencies:
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_01 | Check user registration with an existing username | Attempt to register using an existing username | 1. In the registration page, attempt to register using an existing username. | Existing username: admin; member | Error message: "Username already exists." | User remains on registration page | Username already exists error displayed correctly. | Pass
2. Enter the username, password, and choose account type

## Check user login with invalid c
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Check user login with invalid credentials | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | User is in the login page
Dependencies:
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_02 | Check user login with invalid credentials | Attempt to login using a wrong username and password | 1. In the login page, attempt to login using a wrong username or password | Username: admin1; member1, Password; wrongpass | Error message: "Invalid username or password." | User remains on login page | Error displayed: "Invalid username or password." | Pass
2. Enter the username and password

## As a guest user check “Members
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | As a guest user check “Members Only” button in side bar | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | User is in the dashboard page
Dependencies:
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_03 | As a guest user check “Members Only” button in side bar | Check if “Members Only” button ask the user to sign in | In the dashboard page, try to click "Members Only" |  | Redirect to sign-in page. | Guest user remains unauthenticated | Sign-in prompt displayed when button clicked. | Pass

## As a guest user check "Forum" b
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | As a guest user check "Forum" button in side bar | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | User is in the dashboard page
Dependencies:
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_04 | As a guest user check "Forum" button in side bar | Check if "Forum" button ask the user to sign in | In the dashboard page, try to click "Forum" |  | Redirect to sign-in page. | Guest user remains unauthenticated | Sign-in prompt displayed when button clicked. | Pass

## Check “Add Article” form has ap
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Check “Add Article” form has appropriate fields | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | As an admin, user is in the "Add Article" page
Dependencies:
Test Priority | High
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_05 | Check “Add Article” form has appropriate fields | Checking form functionality and if the corresponding fields have appropriate entry types (date, dropdown, text, etc.) | Using an admin account, open the "Add Article" form and inspect fields. |  | All fields displayed correctly (e.g., title as text, date as date picker). | Form loaded successfully | Form fields display correctly with appropriate types. | Pass

## Check “Add Book” form has appro
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Check “Add Book” form has appropriate fields | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | As an admin, user is in the "Add Book" page
Dependencies:
Test Priority | High
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_06 | Check “Add Book” form has appropriate fields | Checking form functionality and if the corresponding fields have appropriate entry types (date, dropdown, text, etc.) | Using an admin account, open the "Add Book" form and inspect fields. |  | All fields displayed correctly (e.g., title as text, date as date picker). | Form loaded successfully | Form fields display correctly with appropriate types. | Pass

## Check “Add Research Paper” form
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Check “Add Research Paper” form has appropriate fields | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | As an admin, user is in the "Add Research Paper" page
Dependencies:
Test Priority | High
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_07 | Check “Add Research Paper” form has appropriate fields | Checking form functionality and if the corresponding fields have appropriate entry types (date, dropdown, text, etc.) | Using an admin account, Open the "Add Research Paper" form and inspect fields. |  | All fields displayed correctly (e.g., title as text, date as date picker). | Form loaded successfully | Form fields display correctly with appropriate types. | Pass

## Check “Add Video” form has appr
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Check “Add Video” form has appropriate fields | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | As an admin, user is in the "Add Video" page
Dependencies:
Test Priority | High
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_08 | Check “Add Video” form has appropriate fields | Checking form functionality and if the corresponding fields have appropriate entry types (date, dropdown, text, etc.) | Using an admin account, Open the "Add Video" form and inspect fields. |  | All fields displayed correctly (e.g., title as text, date as date picker). | Form loaded successfully | Form fields display correctly with appropriate types. | Pass

## Validate role-based content acc
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Validate role-based content access | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | User is in the dashboard page
Dependencies:
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_09 | Validate role-based content access | Ensure only authorized roles (member, admin) can access exclusive content | Attempt to access exclusive content with different user roles. | Role: Guest, Role: Member | Only authorized users (members or admins) can access; unauthorized users see access restricted message. | Access restricted for guest | Access restricted message displayed for guest user. | Pass
Member Credentials:
Username: Member
Password: 123

## Check content creation for admi
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Check content creation for admins only | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | User is in the dashboard page
Dependencies:
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_10 | Check content creation for admins only | Ensure that only users with admin rights can access the content creation interface | Log in as non-admin and attempt to access content creation interface. | Role: Admin, Role: Member; Guest | Only admin users can access content creation; other users see access restricted message. | Access restricted for non-admin | Non-admin cannot access content creation. | Pass
Admin Credential:
Username: Admin
Password: 123

## Check the “Create new post” but
BWP | Project Name: | Online Bamboo Catalog | Test Designed by: Dave Aldrin B Alia
| Module Name: | Check the “Create new post” button on Forum | Test Designed date: November 05, 2024
| Release Version: | 1 | Test Executed by: Johanne Marlowe E. Sanchez
Test Execution date: November 06, 2024
Pre-condition | User is in the dashboard page
Dependencies:
Test Priority | Medium
Test Case# | Test Title | Test Summary | Test Steps | Test Data | Expected Result | Post-condition | Actual Result | Status | Notes
TC_11 | Check the “Create new post” button on Forum | Confirm the "Create new post" button on the forum redirects to the post creation form | Click the "Create new post" button on the forum. | Role: Admin; Member | Redirects to post creation form with relevant fields (title, content, etc.) | User is ready to create a post | Post creation form opens with fields displayed. | Pass
Admin Credentials: Username: Admin Password: 123 Member Credentials: Username: Member Password: 123